## Ownership in the Line (hidden)
Green Light Session
Objective: Cement the process in the line.
What do we need to do to make this happen?
Phased Approach:
Phase 1 - Continue to heighten awareness - (12 months)
Phase 2 - Identify training requirements and do training - (12 months)
Phase 3 - Hand off your process role to line and you will act as a consultant - (6 months)
Phase 4 - New environment fostered - Who are you - find another job.
Include as responsibility/accountability on ICA/OBJ with associated measures.
Include in Job Models
Recognize training requirements - facilitation, overview of process (RBG)
Entrench in group meetings process and gaps (broken items)
At section level communicate importance of process and that the responsibility lies at the section,
team and individual.
Re-focus process from Tier C to D to E
Develop a template checklist that recognizes how to fix the process
Put pressure on employees to keep process in their face
Increase the energy and desire to work on process
Anyone should be able to address/identify gaps
Recognize skill levels in section to educate members on what a gap looks like
Monthly Themed Communication Seminars
Feb - Process Prime Communication Plan
Mar - Customers, who they are and how to identify their needs Prime Dave McKenna
Apr - Gaps
May - Measures
Jun - CSA
Jul - Scorecard
Aug - Leading and Lagging Measures
Sep - Maps
Oct - Section Business Plan
Nov - Job Models
Dec - Year End Review
Plan is to have a prime per month who will develop the initial communication seminar package
and each prime will manipulate to meet their section needs.
Feb will be scoped out on Feb 11 meeting
Dave M will send out his AIO (March package) for discussion on Feb 11

## CSA Requirements (hidden)
Target Group (who is it and why do it) | Prime | DueDate | Measures
NCC Target Ntwk focus in NCC | Murray | Nov | Decrease in overdue orders and decrease in change orders by NCC Tech
Sales (MCS) - quality of MCIP packages | Murray | Nov
IS/IT - Support documentation without funding | Murray | Nov
This could be a process gap Gerry to investigate |  | June
BFCO - response time re commissioning | Gerry B | Dec | Remove extended time frame (improve cycle time of completed job)
IS&P group ??? | Brian | Dec | Brian will update by end of Feb
NDI - re service manager response for funding | Brian | Dec
Ntwk Mtce -they do provisioning in the field | Brian | Dec
LPAG - turn around times | Brian | Dec
Data shop - turn around and response time | Brian | Dec
Capacity Mgmt - response/product/communication | Brian | Dec
Expertech - quality of service - response time | Brian | Dec
NIC & FOM - quality audits - set the parameters | Brian | Dec
NCR - quality and response time | Brian | Dec
NPCO - (project mgmt grp) handoffs and timing not | Brian | Dec
FMS - new service intro | Brian | Dec
NSRC - quality | Brian | Dec
Transport - firm up the reservation of T1 links and | Dave | Dec | Completed
define reservation policy (perhaps closing the
process gap - common understanding)
Traffic Ntwk Mgmt - evaluate initial CSA | Anne | Dec
If enhanced CSA required (timing and handoffs
between Traffic and Ntwk Mgmt (Switch and Access) |  | Dec

## Agenda 01-20 (hidden)
District Process Team Meeting
| Date: | 2003-01-20
| Time: | 9:30 | to | 12:05
Conference Bridge #:
Chair Person #:
Participant #:
| Facilitator: |  | Dave
| Time Keeper: |  | Anne
| Note Taker: |  | Ryan
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 | 0:00 | 9:30 | 9:30 | Welcome and Review Agenda | All | Information Sharing
2 | 0:05 | 9:30 | 9:35 | Review Norms | All | Information Sharing
3 | 0:05 | 9:35 | 9:40 | Review Agenda Items | All | Information Sharing
4 | 0:05 | 9:40 | 9:45 | Review minutes of last meeting | All | Information Sharing
5 | 0:15 | 9:45 | 10:00 | Action Register | All | Discussion
6 | 0:45 | 10:00 | 10:45 | Support Implementation Design Project | Larry | Information Sharing
7 | 0:15 | 10:45 | 11:00 | Break
8 | 0:10 | 11:00 | 11:10 | Business Plan | All | Discussion
9 | 0:15 | 11:10 | 11:25 | Create a Mandate | All | Discussion
10 | 0:20 | 11:25 | 11:45 | Create Norms | All | Discussion
11 | 0:10 | 11:45 | 11:55 | Discuss Items Surrounding the Agenda ie. Locked in Items | All | Discussion
12 | 0:05 | 11:55 | 12:00 | Review Last Meeting | All | Discussion
13 | 0:05 | 12:00 | 12:05 | Review "Risk" presentation Training | All | Discussion
14 |  | 12:05 | 12:05
15 |  | 12:05 | 12:05
16 |  | 12:05 | 12:05
17 |  | 12:05 | 12:05
18 |  | 12:05 | 12:05
19 |  | 12:05 | 12:05
20 |  | 12:05 | 12:05
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 01-20 (hidden)
Meeting Minutes
Facilitator: | Dave | Notetaker: | Ryan | Timekeeper: | Anne
Attendees:
Dave | Ryan | Anne | Murray | Larry
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
Review Minutes of last meeting | 1) Develop Risk Presentation - In progress. 2) Ryan to update Action Register with meeting agendas and meeting minutes. 3) To keep visibility within the District, the District Process Team will publish their work quarterly within a Power Point Presentation. Ryan is to insert an empty presentation file within the Process folder on the O drive. 4) The District Process Team will send a formal invitation to the other sections that are currently not represented at the meetings.
L2 Redefine | 1) Design Phase is complete. 2) Currently working on the Implementation Design Phase. 3) Defined Corporate vs. Local Application and Major vs. Minor Application. 4) Created a list of all the support committees.
Business Plan | 1) Team has decided to use our Action Register as our Business Plan. This will keep everything within one document. Consequently a "BP" field will be added to the Action Register to flag items that are Business Plan related.
Agenda Items | 1) There are 3 items that will make a regular monthly appearance on the agendas. They will be "Review the Minutes of the Last Meeting", "Action Register", "Quarterly District Meeting Updates".
Create a Mandate | 1) Ladies and gentlemen we have an new mandate… Check the "Mandate" TAB within this document
Create Norms | 1) Discussed and agreed on a set of Meeting Norms to be used during each meeting. Check the "Meeting Norms" TAB within this document.
Date of Next Meeting: |  | 2003-02-10
Roles For Next Meeting:
Facilitator: | Ryan | Notetaker: | Anne | Timekeeper: | Murray
Meeting Evaluation: |  | Good, Concise, To the point

## Agenda 02-10 (hidden)
District Process Team Meeting
| Date: | 2003-02-10
| Time: | 9:30 | to | 12:00
| Location: |  | Room:
|  | Conference Bridge #: |  | 1-866-540-8130
Chair Person #:
|  | Participant #: |  | 6270925#
| Facilitator: |  | Ryan
| Time Keeper: |  | Murray
| Note Taker: |  | Anne
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 | 0:05 | 9:30 | 9:35 | Welcome and Review Agenda | All | Information Sharing
2 | 0:05 | 9:35 | 9:40 | Review Norms | All | Information Sharing
3 | 0:05 | 9:40 | 9:45 | Review Agenda Items | All | Information Sharing
4 | 0:10 | 9:45 | 9:55 | Review minutes of last meeting | All | Information Sharing
5 | 0:15 | 9:55 | 10:10 | Action Register | All | Discussion
6 | 0:20 | 10:10 | 10:30 | Talk about the action register - do we want all of these tabs. (What's with the long file name.) | Team | Discussion
7 | 0:15 | 10:30 | 10:45 | Break
8 | 0:20 | 10:45 | 11:05 | L2 Redefine | Larry | Information Sharing
9 | 0:25 | 11:05 | 11:30 | Risk Presentation | Dave | Discussion
10 | 0:30 | 11:30 | 12:00 | Tier D Scorecard | Ryan | Information Sharing
11 |  | 12:00 | 12:00
12 |  | 12:00 | 12:00
13 |  | 12:00 | 12:00
14 |  | 12:00 | 12:00
15 |  | 12:00 | 12:00
16 |  | 12:00 | 12:00
17 |  | 12:00 | 12:00
18 |  | 12:00 | 12:00
19 |  | 12:00 | 12:00
20 |  | 12:00 | 12:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 02-10 (hidden)
Meeting Minutes February 10 2003
Facilitator: | Ryan | Notetaker: | Anne | Timekeeper: | Murray
Attendees: | Ryan, Dave, Anne & Murray
Regrets (Absent): | na
AGENDA ITEM | NOTES/ACTION REQUIRED
5 The Action Register | Mechanized Scorecard; Ryan provided an update on the Transport District's mech scorecard (Steve Scott Tools & Measures prime) status. Transport is currently utilizing the tool for Department/District Tactical reporting only, currently not usable for Tier D/E Objective Perfromence Reporting. Action: Ryan to request a presentation by Steve Scott at the next Process Pals Mtg March 10 with focus on 2 items i) selling/marketing the automated tool ii) what the benefits would be to transfer to this tool for a District with functional Scorecards already in place Ryan confirmed Feb 12 of Steve's availability for March 10 F2F - location is Creekbank (if that suits everyone).
Risk Presentation; this item is Parked until discussion with Joanne Doust re Department involvement Update Feb 12; Dave & Anne met with Joanne & determined roles & responsibilities. Dave will issue a copy of our little Risk Presentation to the reps in Transport etc & they can determine if it is what they wanted or, if those primes need to develop their own. Joanne to confirm email distribution contacts. Action; Dave to issue Risk Presentation to this distribution Raoul W. etc.
6 The Action Register Format | Action; Ryan to 'hide" 2002 closed/historical items and only keep current tabs viewable including current month +1 and ii) Ryan to create a tab to contain the Process Pals 2003 Mandate
8 Redefine Project | Update from Larry; slides now posted to Process folder O drive + emailed Feb 11. Larry provided Redesign url address http://sarnet.qc.bell.ca/redefine_support/. All presentations located on this website. New communication package under development & will be available later this week. No action items for the Process Pals this week.
1 Review Minutes from Jan meeting | Action; Murray to follow up with BB/IP teams to determine if they want to send a member to this forum
Date of Next Meeting:
March 10, 2003
Roles For Next Meeting:
Facilitator: | Anne | Notetaker: | Murray | Timekeeper: | Dave
Meeting Evaluation: |  | good - shorter than planned!

## Agenda 03-10 (hidden)
District Process Team Meeting
| Date: | March 10, 2003
| Time: | 10:00 | to | 12:00
| Location: |  | Room: | n/a
|  | Conference Bridge #: |  | 1-866-540-8130
Chair Person #:
|  | Participant #: |  | 6256724#
| Facilitator: |  | Anne
| Time Keeper: |  | Murray
| Note Taker: |  | Dave
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 | 0:05 | 10:00 | 10:05 | Welcome & Review Agenda | Anne
2 | 0:25 | 10:05 | 10:30 | Review Feb 10 Minutes | all
3 | 0:15 | 10:30 | 10:45 | Review & Update Action Register | all
4 | 0:15 | 10:45 | 11:00 | L2 Redefine Project Update | Larry B.
5 | 0:15 | 11:00 | 11:15 | BREAK | all
6 | 0:15 | 11:15 | 11:30 | Updates for District Process Web site | Murray
7 | 0:15 | 11:30 | 11:45 | Plan Apr 3rd F2F Process Mtg | all
8 |  | 11:45 | 11:45
9 |  | 11:45 | 11:45
10 |  | 11:45 | 11:45
11 |  | 11:45 | 11:45
12 |  | 11:45 | 11:45
13 |  | 11:45 | 11:45
14 |  | 11:45 | 11:45
15 |  | 11:45 | 11:45
16 |  | 11:45 | 11:45
17 |  | 11:45 | 11:45
18 |  | 11:45 | 11:45
19 |  | 11:45 | 11:45
20 |  | 11:45 | 11:45
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 03-10 (hidden)
Meeting Minutes March 10, 2003
Facilitator: | Anne | Notetaker: | Murray | Timekeeper: | Dave
Attendees: | Dave, Anne & Murray
Regrets (Absent): | Ryan
AGENDA ITEM | NOTES/ACTION REQUIRED
5 The Action Register | Mechanized Scorecard; Ryan provided an update on the Transport District's mech scorecard (Steve Scott Tools & Measures prime) status. Transport is currently utilizing the tool for Department/District Tactical reporting only, currently not usable for Tier D/E Objective Perfromence Reporting. Action: Ryan to request a presentation by Steve Scott at the next Process Pals Mtg March 10 with focus on 2 items i) selling/marketing the automated tool ii) what the benefits would be to transfer to this tool for a District with functional Scorecards already in place Ryan confirmed Feb 12 of Steve's availability for April 03/03 @ 10am F2F - location is Creekbank (if that suits everyone).
Risk Presentation; this item is Parked until discussion with Joanne Doust re Department involvement Update Feb 12; Dave & Anne met with Joanne & determined roles & responsibilities. Dave will issue a copy of our little Risk Presentation to the reps in Transport etc & they can determine if it is what they wanted or, if those primes need to develop their own. Joanne to confirm email distribution contacts. Action; Dave to issue Risk Presentation to this distribution Raoul W. etc. Dave presented to Transport Process Mgrs & Assocs Mar 03/903. Well received. Dave to followup with J.Doust re. closing the loop on this topic.
6 The Action Register Format | Action; Ryan to 'hide" 2002 closed/historical items and only keep current tabs viewable including current month +1 and ii) Ryan to create a tab to contain the Process Pals 2003 Mandate. CLOSED.
8 Redefine Project | Update from Larry; slides now posted to Process folder O drive + emailed Feb 11. Larry provided Redesign url address http://sarnet.qc.bell.ca/redefine_support/. All presentations located on this website. New communication package under development & will be available later this week. No action items for the Process Pals this week. Larry presenting to Tier Bs today Mar 10/03. Update to follow.
1 Review Minutes from Jan meeting | Action; Murray to follow up with BB/IP teams to determine if they want to send a member to this forum Murray to send minutes to Charles & Jim.
Ryan | Ryan to find Jan/03 minutes and put into XLS. file (new tab)
Ryan | Ryan determine Steve Scott's requirements for Apr/03 meeting. Is there anything that the Process team needs to do prior ??
Date of Next Meeting:
April 03, 2003
Roles For Next Meeting:
Facilitator: | Murray | Notetaker: | Dave | Timekeeper: | Ryan
Meeting Evaluation: |  | MV - productive. AM - no bagels. DM - good.

## Agenda 04-03 (hidden)
District Process Team Meeting
| Date: | 2003-04-03
| Time: | 10:00 | to | 3:00PM
| Location: |  | Room: | Creekbank Room CB2 (lower level)
Conference Bridge #:
Chair Person #:
Participant #:
| Facilitator: |  | Murray
| Time Keeper: |  | Ryan
| Note Taker: |  | Dave
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 | 1:00 | 10:00 | 11:00 | Steve Scott presentation | Ryan
2 | 0:45 | 11:00 | 11:45 | Create Bus Plan for 2003 | All
3 | 0:30 | 11:45 | 12:15 | How do we make ourselves more public - raise profile ?? | Dave
4 | 0:30 | 12:15 | 12:45 | Lunch | All
5 | 0:15 | 12:45 | 13:00 | Minute taker must send note to Jerome each month | TBD
6 | 0:30 | 13:00 | 13:30 | Update on web page | Murray
7 | 0:30 | 13:30 | 14:00 | Larry update (confirm time slot) | All
8 |  | 14:00 | 14:00
9 |  | 14:00 | 14:00
10 |  | 14:00 | 14:00
11 |  | 14:00 | 14:00
12 |  | 14:00 | 14:00
13 |  | 14:00 | 14:00
14 |  | 14:00 | 14:00
15 |  | 14:00 | 14:00
16 |  | 14:00 | 14:00
17 |  | 14:00 | 14:00
18 |  | 14:00 | 14:00
19 |  | 14:00 | 14:00
20 |  | 14:00 | 14:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 04-03 (hidden)
Meeting Minutes April 3, 2003
Facilitator: | Murray | Notetaker: | Dave | Timekeeper: | Ryan
Attendees:
Regrets (Absent): | Larry Benedet
AGENDA ITEM | NOTES/ACTION REQUIRED
1 | Mechanized Scorecard (Steve Scott Tools & Measures prime) Steve Scoot gave a presentation of the automated (TNI) Transport Scorecard. It was noted that the TNI scorecard can drill down to tier “D” and therefore the individual can understand and appreciate how their personal activates impact the district scorecard. As well in the future it will be used with regards to the Objective Performance for “tier” “D”. Next Steps for the process pals – talk to Gord – how can we adapt this to our section(s). Is there anything here we can use. ACTION ITEM: Ryan to engage Gord Lange and establish "next steps" from a mechenization perspective. ACTION ITEM: Dave to get .ppt from Steve and he link to their scorecard. Continue investigating using the TNI type of scorecard. At least get it into access. Gord can call Steve anytime. Other team members – Brad Jones, Kristin Lucy.
2 | It was agreed by the team that the process bus plan for 2003 will not be created - we will use the action register as the BP.
3 | First quarter .PPT - what we have done – what we are working on etc. One page high-level .PPT for “C” and “B”. The team created a .PPT at the meeting. Ryan to create the .PPT and send to the team to review.
6 | Process WEB page (Murray) is being updated by no one at this time (i.e. their is not a prime) – Murray is going to talk with Andrew Chin and let the team know if he can do the updates on the WEB page. Ryan to see if he can take a course on building WEB pages then he could make the updates for us – Ryan to update for next meeting.
ONMP – are their users in our district that this will affect. I.e. are their impacts with our teams. Action Item: Each of the process pals to send a note to their section asking for any impact. Send the .PPT but be sure that in the body of the note that TARS is being replaced. They may want to go to their TARS support person if they want input.
Mics | One of the process pals (not to be name here) mentioned that it might be appropriate to bring “more” than 20 timbits.
Date of Next Meeting: |  | May 12, 2003
Roles For Next Meeting:
Facilitator: | Dave | Notetaker: | Ryan | Timekeeper: | Anne
Meeting Evaluation:
Note on C13: David McKenna: Gord to give our team an update as to moving our scorecard to the dbase. (By end of May for assessment – how does it work today, i.e. how many people working on the scorecard today versus tomorrow)
Note on C15: David McKenna: First quarter process update – send this to Ryan (he will send to the PP first to review) List our mandate Ryan. · Developed risk presentation – rollout in qtr 2 and 3. · Evaluate Automated balanced scorecard solution. · Assisted with the OSS definition for the NP Redefine Project. · Development of CSA between o Translations and NCC. o Switch with access.

## Agenda Jun-09 (hidden)
District Process Team Meeting
| Date: | 2003-06-09
| Time: | 9:00 | to | 10:30
| Location: |  | Room: | n/a
|  | Conference Bridge #: |  | 416-343-2578 or 866-235-8288
Chair Person #:
|  | Participant #: |  | 7565052 #
| Facilitator: |  | David
| Time Keeper: |  | Murray
| Note Taker: |  | Anne
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 | 0:05 | 9:00 | 9:05 | Welcome & Review Agenda | David
2 | 0:25 | 9:05 | 9:30 | Review April 10 Minutes | all
3 | 0:15 | 9:30 | 9:45 | Review & Update Action Register | all
4 | 0:10 | 9:45 | 9:55 | L2 Redefine Project Update | David
5 | 0:10 | 9:55 | 10:05 | Updates for District Process Web site | Murray
6 | 0:10 | 10:05 | 10:15 | Risk Assessment Update | All
7 | 0:15 | 10:15 | 10:30 | Open items | All
8 |  | 10:30 | 10:30
9 |  | 10:30 | 10:30
10 |  | 10:30 | 10:30
11 |  | 10:30 | 10:30
12 |  | 10:30 | 10:30
13 |  | 10:30 | 10:30
14 |  | 10:30 | 10:30
15 |  | 10:30 | 10:30
16 |  | 10:30 | 10:30
17 |  | 10:30 | 10:30
18 |  | 10:30 | 10:30
19 |  | 10:30 | 10:30
20 |  | 10:30 | 10:30
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes Jun-09 (hidden)
Meeting Minutes June 9, 2003
Facilitator: | Dave | Notetaker: | Anne | Timekeeper: | Murray
Attendees: | Dave, Ryan, Murray (sans laptop) & Anne
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
1 | Welcome & Review
2 | Review Previous Minutes: Enhanced Automated Scorecard Feasibility: Ryan & Gord met with Steve Scott/ next step understand all measures in District Section teams; waiting for new functionality of NP OTOV card; follow up with Gord to obtain NP OTOV timelines. Process Pals will then determine next steps & timelines
3 | Review & Update Action Register: Dave updated the Action Register
4 | L2 Redefine: Roadshow rolled out to Ottawa Tier C's, London rollout scheduled June 17, no info on Toronto schedule; Dave to obtain Roadshow Schedule from Larry
5 | Process District Web Site Status Update: Murray to set up impromptu mtg with Andrew Chin - Murray to advise netmtg date in June 2003.
6 | Risk Assessment Status Update: suggestion from Dave's rollout - have teams analyze all job function maps/tasks to determine if Risk applicable
7 | II QTR Communication Update: create the update via Wed July 9th at 1:30 conf call
Date of Next Meeting: |  | Sept 8, 2003
Roles For Next Meeting: |  | F2F
Facilitator: | Ryan | Notetaker: | Murray | Timekeeper: | Anne
Meeting Evaluation:

## assumptions & questions
SWAG:
Cost | 500K
Timeline | 7 months
What we know | What we think we know (Assumptoins) | What we don't Know (Questions) | <-- Who to ask | Prime to get answer | Date for answers | Open or answered
| Customers are willing to pay a premium for sustainable and eco-friendly jackets. |  |  | Conduct market research and customer surveys to gauge customer interest and willingness to pay.
The sustainable materials chosen for the jackets will meet quality and durability requirements. |  |  |  | Perform material testing and quality control checks during the manufacturing process.
|  | Manufacturers and suppliers have the capacity and capability to produce the sustainable jackets at the desired scale. |  | Conduct Quality Testing and Evaluate sustainable practice
| The sustainable jackets will meet relevant industry regulations and certifications. |  |  | Research applicable Certifications and regulations to ensure that regulations and standards are met
| The sustainable jackets will be marketed effectively to reach the target audience. |  |  | Develop and effective and comprehensive marketing strategy
| The sustainable jackets will have a positive environmental |  |  | Conduct assesment and develop carbon footprint tracker.

## mini budget
Name | WC | Group | Cost
Management Reserve (10%) |  |  | 50000 | <-- this is a one time cost
Contingency Reserve (15%) |  |  | 67500
Activities Reserve |  |  | 38250
Human Resources |  |  | 7000
Materials |  |  | 30250
Outsourcing |  |  | 174000
Human Resources |  |  | 100000
Marketing |  |  | 8000
Delivery and Shipment |  |  | 25000
|  | TOTAL | 500000

## Budget
Project Name: Sustainable Jacket
Employee |  | Total Hours | Rate | Total
Total Project Cost (000) --> | 500000
Reserves
Management Reserve |  |  |  | 50000
Contingency Reserve |  |  |  | 67500
Activity Reserve |  |  |  | 38250
Human Resource
Designer 1 |  | 176 | 30 | 5280
Designer 2 |  | 184 | 30 | 5520
Designer 3 |  | 136 | 30 | 4080
CAD Designer |  | 120 | 30 | 3600
Project Manager |  | 528 | 60 | 31680 | u
Product Developer 1 |  | 264 | 16.5 | 4356
Product Developer 2 |  | 280 | 16.5 | 4620
Procurement Manager |  | 256 | 40 | 10240
Logistics Manager |  | 200 | 28 | 5600
Marketing Manager |  | 216 | 30 | 6480
Sample Sewer |  | 112 | 25 | 2800
Sustainability Consultant |  | 208 | 40 | 8320
Business Analyst |  | 168 | 25 | 4200
Pattern Makers |  | 96 | 16.5 | 1584
Logistics Staff |  | 136 | 16.5 | 2244
Sales Manager |  | 24 | 30 | 720
Total |  |  |  | 101324
Materials |  | Qty | Cost | Total
Wool Fabric |  | 150 | 100 | 15000
Thread |  | 15 | 30 | 450
Sketching Materials |  | 2 | 50 | 100
Fasteners and Buttons |  | 5 | 20 | 100
Recycled Polyester |  | 80 | 50 | 4000
Bamboo fleece |  | 100 | 50 | 5000
Zippers |  | 10 | 50 | 500
Cordura |  | 30 | 40 | 1200
Pattern Paper |  | 50 | 15 | 750
Tracing Wheel |  | 60 | 20 | 1200
Pattern Notcher |  | 50 | 20 | 1000
Marking Tools |  | 50 | 25 | 1250
Cotton Ribbing |  | 70 | 50 | 3500
Hosting Subscription |  | 2 | 300 | 600
Domain |  | 1 | 30 | 30
Total |  |  |  | 34680
Cost |  | Qty | Cost | Total
CAD Software |  | 1 | 1000 | 1000
Outsource fee for 2000 Jackets |  | 1 | 150000 | 150000
Air Freight |  | 1 | 4000 | 4000
Sea Freight |  | 1 | 3000 | 3000
Courier Service |  | 1 | 4000 | 4000
Delivery Service for distribution |  | 1 | 5000 | 5000
Logistic Management System |  | 1 | 6000 | 6000
SEO |  | 1 | 3000 | 3000
Influencer Commision Fee |  | 1 | 15000 | 15000
Marketing Collateral |  | 1 | 3746 | 3746
Warehouse |  | 1 | 10000 | 10000
Certification Fees |  | 1 | 2000 | 2000
Contingency Reserve |  | 1 | 67500 | 67500
Management Reserve |  | 1 | 50000 | 50000
Activity Reserve |  | 1 | 38750 | 38750
Social Media Business Subscription |  | 1 | 1000 | 1000
Total |  |  |  | 363996

## R&R
FUNCTIONS
| Designer 1 | Designer 2 | Designer 3 | CAD Designer | Marketing Manager | Logistics Manager | Project Manager | procurement manager | product developer 1 | product developer 2 | sustainability consultant | Pattern maker | sales manager | Sample Sewer | Business Analyst | Logistics Staff
ACTIVITIES
Conduct design analysis: market trend, user preference and branding | I | R | I | I | I | I | A | I | R | I | I | I | I | I | c | I | R esponsible
Establish evaluation criteria for the design selection process | I | I | I | I | C | I | R | I | R | I | I | I | I | I | A | I | A ccountable
Brainstorming of design concepts | R | R | I | I | I | I | A | I | I | I | I | I | I | I | C | I | C onsult
Identify aesthetic requirements: colour, type, and textures | R | R | I | I | C | I | A | I | I | I | I | I | I | I | I | I | I inform
Create a conceptual sketch | C | I | I | I | I | I | A | I | I | R | I | I | I | I | I | I
Conduct design selection process | R | R | I | I | I | I | A | I | I | I | I | I | I | I | I | I
Document and communicate selected design to major stakeholders | C | I | I | I | I | I | A | I | C | I | I | I | I | I | R | I
Final Design Approval | I | I | I | I | I | I | A | I | I | I | I | I | I | I | R | I
Define material requirements to be used for the outer shell, lining, insulation and other components | R | R | I | I | I | I | A | I | I | I | C | I | I | C | I | I
Identify construction techniques to be used for seam and stiching methods | R | I | I | I | I | I | A | I | I | I | C | R | I | C | I | I
Define the features and performance attributes: cushioning, wind resistance, water resistance, and breathability | I | I | R | I | I | I | A | I | I | I | C | R | I | I | I | I
Established sizing system and fit specifications | I | I | R | I | I | I | A | I | I | I | I | C | I | I | I | I
Select fastener sand closure system to be used in the jacket | I | R | I | I | I | I | A | I | I | I | I | C | I | I | I | I
Document all the technical requirements | R | I | I | I | I | I | C | I | R | I | I | I | I | I | A | I
Research materials that are eco-friend and sustainable | I | I | I | I | I | I | A | I | I | I | R | C | I | C | I | I
Identify areas to reduce waste through our design and production process | I | I | I | I | I | I | R | I | C | I | I | I | I | I | A | I
Established carbon footprint tracker | C | I | I | I | I | I | A | I | I | R | R | I | I | I | I | I
Obtain compliance certificate from Canadian Safety regulations | I | C | I | I | I | I | A | I | R | I | R | I | I | I | I | I
Determine the labelling in compliance with regulations and standards. | R | I | I | I | I | I | A | I | I | I | R | I | I | I | C | I
Create 2D drawings using AutoCAD sofware | C | I | I | R | I | I | A | I | I | I | C | I | I | I | I | I
Incorporate material specification, aesthetics, and sizing systems as mentioned in the design documents | I | R | C | R | I | I | A | I | I | I | I | I | I | I | I | I
Create a 3D model to simulate visualization and Virtual fitting. | I | R | I | R | I | I | A | I | C | I | I | I | I | I | I | I
Evaluate, Iterate and refine the 3D model | R | I | R | R | I | I | A | I | I | C | I | I | I | I | I | I
Select a sample makers to do the prototype version | I | I | I | I | I | I | R | I | I | I | I | I | I | C | A | I
Material Selection and Sourcing | I | I | I | I | I | I | A | R | I | I | I | I | I | C | I | I
Create pattern templates | I | I | I | I | I | I | A | I | I | I | I | R | I | C | I | I
Cutting fabrics and assembly of fabric pieces | I | I | I | I | I | I | A | I | I | I | I | C | I | R | I | I
Produce several samples | I | I | I | I | I | I | A | I | I | I | I | C | I | R | I | I
Conduct Focus Group to test functionality | I | I | I | I | R | I | I | I | I | R | I | I | C | I | A | I
Refinement and Iteration | I | I | R | I | I | I | A | I | I | I | I | I | I | R | C | I
Create a short list of potential manufacturers | I | I | I | I | I | R | A | R | I | I | I | I | I | I | C | R
Send Request for Proposals (RFPs) to the manufacturers | I | I | I | I | I | I | A | R | I | I | I | I | I | I | C | I
Evaluate proposals and select manufacturer | I | I | I | I | I | I | A | R | I | I | I | I | I | I | C | I
Contract negotiation | I | I | I | I | I | I | A | R | I | I | I | I | I | I | C | I
Develop scheduling plan | I | I | I | I | I | I | R | I | I | I | I | I | I | I | C | I
Develop a quality assurance process | I | I | I | I | I | I | C | I | R | I | I | I | I | I | A | I
Review the manufacturer's raw materials sourcing | I | I | C | I | I | I | A | I | R | I | R | I | I | I | I | I
Production Starts | bar: I I to I I
Monitor the scheduling plan | I | I | I | I | I | I | A | I | I | R | I | I | I | I | C | I
Track the inventory levels | I | I | I | I | I | R | A | C | I | I | I | I | I | I | I | I
Quality Assurance and Inspection | I | I | I | I | I | I | A | I | R | R | I | I | I | I | C | I
Receive delivery | I | I | I | I | I | R | A | C | I | I | I | I | I | I | I | I
Develop a brand name | I | I | I | I | R | I | A | I | I | I | I | I | I | I | C | I
Design logo | R | I | I | R | C | I | C | I | I | I | I | I | I | I | A | I
Create a brand story that communicates sustainability and company values | C | I | I | I | R | I | A | I | I | I | I | I | I | I | C | I
Create brochures and flyers | I | I | I | I | A | I | C | I | R | I | I | I | I | I | I | I
Create website content | I | I | I | I | R | I | A | I | C | I | I | I | I | I | C | I
Develop social media strategy on various platforms | I | I | I | I | A | I | C | I | I | R | I | I | I | I | I | I
Hire an agency to manage Search Engine Optimization (SEO) | I | I | I | I | R | I | A | I | I | I | I | I | I | I | C | I
Collaborate with influencers who aligns our brand value | I | I | I | I | R | I | A | I | I | I | I | I | I | I | C | I
Evaluate and select Inventory Strategies to be used | I | I | I | I | C | I | A | R | I | I | I | I | I | I | C | I
Identify warehouse and distribution centers | I | I | I | I | C | C | A | I | I | I | I | I | I | I | C | R
Establish inventory control measures | I | I | I | I | I | A | C | I | I | I | I | I | I | I | I | R
Develop Order Processing System | I | I | I | I | C | R | A | I | I | R | I | I | I | I | I | I
Identify Payment Processing System | I | I | I | I | I | I | C | A | R | I | I | I | I | I | I | I
Arrange transportation and shipping services | I | I | I | I | I | I | A | C | I | I | I | I | I | I | C | I
Identify distribution channels: Retail store, e-commerce, and websites | I | I | I | I | I | R | C | A | I | I | I | I | I | I | I | R
Finalize and sign contract agreement | I | I | I | I | I | I | A | R | I | I | I | I | I | I | C | I
Launch Product | I | I | I | I | R | I | A | I | I | I | I | I | R | I | C | I
Evaluate product and sales performance | I | I | I | I | I | I | A | I | R | R | I | I | R | I | C | I

## Agenda 04-07 (hidden)
District Process Team Meeting
| Date: | 2003-04-04
| Time: | 0:00 | to | 0:00
| Location: |  | Room:
Conference Bridge #:
Chair Person #:
Participant #:
Facilitator:
Time Keeper:
Note Taker:
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 |  |  | 0:00
2 |  | 0:00 | 0:00
3 |  | 0:00 | 0:00
4 |  | 0:00 | 0:00
5 |  | 0:00 | 0:00
6 |  | 0:00 | 0:00
7 |  | 0:00 | 0:00
8 |  | 0:00 | 0:00
9 |  | 0:00 | 0:00
10 |  | 0:00 | 0:00
11 |  | 0:00 | 0:00
12 |  | 0:00 | 0:00
13 |  | 0:00 | 0:00
14 |  | 0:00 | 0:00
15 |  | 0:00 | 0:00
16 |  | 0:00 | 0:00
17 |  | 0:00 | 0:00
18 |  | 0:00 | 0:00
19 |  | 0:00 | 0:00
20 |  | 0:00 | 0:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 04-07 (hidden)
Meeting Minutes
Facilitator: |  | Notetaker: | Timekeeper:
Attendees:
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
Date of Next Meeting:
Roles For Next Meeting:
Facilitator: |  | Notetaker: | Timekeeper:
Meeting Evaluation:

## Agenda 05-12 (hidden)
District Process Team Meeting
| Date: | 2003-05-12
| Time: | 0:00 | to | 0:00
| Location: |  | Room:
Conference Bridge #:
Chair Person #:
Participant #:
Facilitator:
Time Keeper:
Note Taker:
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 |  |  | 0:00
2 |  | 0:00 | 0:00
3 |  | 0:00 | 0:00
4 |  | 0:00 | 0:00
5 |  | 0:00 | 0:00
6 |  | 0:00 | 0:00
7 |  | 0:00 | 0:00
8 |  | 0:00 | 0:00
9 |  | 0:00 | 0:00
10 |  | 0:00 | 0:00
11 |  | 0:00 | 0:00
12 |  | 0:00 | 0:00
13 |  | 0:00 | 0:00
14 |  | 0:00 | 0:00
15 |  | 0:00 | 0:00
16 |  | 0:00 | 0:00
17 |  | 0:00 | 0:00
18 |  | 0:00 | 0:00
19 |  | 0:00 | 0:00
20 |  | 0:00 | 0:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 05-12 (hidden)
Meeting Minutes
Facilitator: |  | Notetaker: | Timekeeper:
Attendees:
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
Date of Next Meeting:
Roles For Next Meeting:
Facilitator: |  | Notetaker: | Timekeeper:
Meeting Evaluation:

## Agenda 06-09 (hidden)
District Process Team Meeting
| Date: | 2003-06-09
| Time: | 0:00 | to | 0:00
| Location: |  | Room:
Conference Bridge #:
Chair Person #:
Participant #:
Facilitator:
Time Keeper:
Note Taker:
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 |  |  | 0:00
2 |  | 0:00 | 0:00
3 |  | 0:00 | 0:00
4 |  | 0:00 | 0:00
5 |  | 0:00 | 0:00
6 |  | 0:00 | 0:00
7 |  | 0:00 | 0:00
8 |  | 0:00 | 0:00
9 |  | 0:00 | 0:00
10 |  | 0:00 | 0:00
11 |  | 0:00 | 0:00
12 |  | 0:00 | 0:00
13 |  | 0:00 | 0:00
14 |  | 0:00 | 0:00
15 |  | 0:00 | 0:00
16 |  | 0:00 | 0:00
17 |  | 0:00 | 0:00
18 |  | 0:00 | 0:00
19 |  | 0:00 | 0:00
20 |  | 0:00 | 0:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 06-09 (hidden)
Meeting Minutes
Facilitator: |  | Notetaker: | Timekeeper:
Attendees:
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
Date of Next Meeting:
Roles For Next Meeting:
Facilitator: |  | Notetaker: | Timekeeper:
Meeting Evaluation:

## Agenda 09-08 (hidden)
District Process Team Meeting
| Date: | 2003-09-08
| Time: | 0:00 | to | 0:00
| Location: |  | Room:
Conference Bridge #:
Chair Person #:
Participant #:
Facilitator:
Time Keeper:
Note Taker:
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 |  |  | 0:00
2 |  | 0:00 | 0:00
3 |  | 0:00 | 0:00
4 |  | 0:00 | 0:00
5 |  | 0:00 | 0:00
6 |  | 0:00 | 0:00
7 |  | 0:00 | 0:00
8 |  | 0:00 | 0:00
9 |  | 0:00 | 0:00
10 |  | 0:00 | 0:00
11 |  | 0:00 | 0:00
12 |  | 0:00 | 0:00
13 |  | 0:00 | 0:00
14 |  | 0:00 | 0:00
15 |  | 0:00 | 0:00
16 |  | 0:00 | 0:00
17 |  | 0:00 | 0:00
18 |  | 0:00 | 0:00
19 |  | 0:00 | 0:00
20 |  | 0:00 | 0:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 09-08 (hidden)
Meeting Minutes
Facilitator: |  | Notetaker: | Timekeeper:
Attendees:
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
Date of Next Meeting:
Roles For Next Meeting:
Facilitator: |  | Notetaker: | Timekeeper:
Meeting Evaluation:

## Agenda 11-10 (hidden)
District Process Team Meeting
| Date: | 2003-11-10
| Time: | 0:00 | to | 0:00
| Location: |  | Room:
Conference Bridge #:
Chair Person #:
Participant #:
Facilitator:
Time Keeper:
Note Taker:
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 |  |  | 0:00
2 |  | 0:00 | 0:00
3 |  | 0:00 | 0:00
4 |  | 0:00 | 0:00
5 |  | 0:00 | 0:00
6 |  | 0:00 | 0:00
7 |  | 0:00 | 0:00
8 |  | 0:00 | 0:00
9 |  | 0:00 | 0:00
10 |  | 0:00 | 0:00
11 |  | 0:00 | 0:00
12 |  | 0:00 | 0:00
13 |  | 0:00 | 0:00
14 |  | 0:00 | 0:00
15 |  | 0:00 | 0:00
16 |  | 0:00 | 0:00
17 |  | 0:00 | 0:00
18 |  | 0:00 | 0:00
19 |  | 0:00 | 0:00
20 |  | 0:00 | 0:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 11-10 (hidden)
Meeting Minutes
Facilitator: |  | Notetaker: | Timekeeper:
Attendees:
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
Date of Next Meeting:
Roles For Next Meeting:
Facilitator: |  | Notetaker: | Timekeeper:
Meeting Evaluation:

## Agenda 12-15 (hidden)
District Process Team Meeting
| Date: | 2003-12-15
| Time: | 0:00 | to | 0:00
| Location: |  | Room:
Conference Bridge #:
Chair Person #:
Participant #:
Facilitator:
Time Keeper:
Note Taker:
ITEM | TIME |  |  | TOPIC | PRIME | REASON
Which | How Long |  |  | What | Who | Why
| Duration | Start Time | End Time
1 |  |  | 0:00
2 |  | 0:00 | 0:00
3 |  | 0:00 | 0:00
4 |  | 0:00 | 0:00
5 |  | 0:00 | 0:00
6 |  | 0:00 | 0:00
7 |  | 0:00 | 0:00
8 |  | 0:00 | 0:00
9 |  | 0:00 | 0:00
10 |  | 0:00 | 0:00
11 |  | 0:00 | 0:00
12 |  | 0:00 | 0:00
13 |  | 0:00 | 0:00
14 |  | 0:00 | 0:00
15 |  | 0:00 | 0:00
16 |  | 0:00 | 0:00
17 |  | 0:00 | 0:00
18 |  | 0:00 | 0:00
19 |  | 0:00 | 0:00
20 |  | 0:00 | 0:00
0:00
0:05 | [5 empty] | Presentation
0:10 | [5 empty] | Discussion
0:15 | [5 empty] | Information Sharing
0:20 | [5 empty] | Recognition
0:25 | [5 empty] | Training
0:30
0:35
0:40 |  |  |  | Room:
0:45
0:50 |  |  |  | Facilitator:
0:55
1:00
1:05
1:10
1:15
1:20
1:25
1:30
1:35
1:40
1:45
1:50
1:55
2:00
2:15
2:30
2:45
3:00

## Minutes 12-15 (hidden)
Meeting Minutes
Facilitator: |  | Notetaker: | Timekeeper:
Attendees:
Regrets (Absent):
AGENDA ITEM | NOTES/ACTION REQUIRED
Date of Next Meeting:
Roles For Next Meeting:
Facilitator: |  | Notetaker: | Timekeeper:
Meeting Evaluation: